Ch 7 Homework Solutions:  Scheduling II

# Problem 7-4

The remainder of the project with F, I, and J all starting at 12 is:

| Activity | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- |
| F | 12 | 17 | 11 | 16 | -1 |
| I | 12 | 15 | 14 | 17 | 2 |
| J | 12 | 17 | 12 | 17 | 0 |
| K | 17 | 19 | 17 | 19 | 0 |
| L | 17 | 20 | 16 | 19 | -1 |

Either F or L must be crashed by one week depending upon which one can be

crashed at least cost.  If resources are taken from another activity, then this must

be activity I, which is the only one having a slack greater than zero.

Problem 7-5

| Activity | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 8 | 10 | 18 | 10 |
| B | 0 | 2 | 10 | 12 | 10 |
| C | 0 | 3 | 0 | 3 | 0 |
| D | 3 | 12 | 3 | 12 | 0 |
| E | 12 | 16 | 14 | 18 | 2 |
| F | 3 | 9 | 9 | 15 | 6 |
| G | 12 | 19 | 12 | 19 | 0 |
| H | 16 | 17 | 18 | 19 | 2 |
| I | 16 | 18 | 23 | 25 | 7 |
| J | 12 | 15 | 12 | 15 | 0 |
| K | 15 | 19 | 15 | 19 | 0 |
| L | 19 | 25 | 19 | 25 | 0 |
| M | 19 | 27 | 21 | 29 | 2 |
| N | 15 | 20 | 24 | 29 | 9 |
| O | 25 | 29 | 25 | 29 | 0 |
| P | 15 | 19 | 33 | 37 | 18 |
| Q | 25 | 28 | 28 | 31 | 3 |
| R | 29 | 31 | 29 | 31 | 0 |
| S | 29 | 30 | 36 | 37 | 7 |
| T | 31 | 37 | 31 | 37 | 0 |

There are two critical paths:

Path 1:  C, D, G, L. O, R, and T

Path 2:  C, D, J, K, L, O, R, and T

Problem 7-6

| Activity | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 3 | 5 | 8 | 5 |
| B | 0 | 8 | 0 | 8 | 0 |
| C | 8 | 12 | 8 | 12 | 0 |
| D | 8 | 10 | 17 | 19 | 9 |
| E | 3 | 4 | 19 | 20 | 16 |
| F | 12 | 19 | 12 | 19 | 0 |
| G | 19 | 24 | 20 | 25 | 1 |
| H | 19 | 25 | 19 | 25 | 0 |
| I | 25 | 33 | 25 | 33 | 0 |
| J | 33 | 42 | 33 | 42 | 0 |

The critical path is:  B, C, F, H, I, and J.

Problem 7-7

Activity C can now be started, but it is 2 weeks late.  Since C is critical, the current slacks	of the activities not started are:

Activity		Slack (weeks)

C		 0 – 2 = -2

D		 9 – 2 = +7

F		 0 – 2 = -2

G		 1 – 2 = -1

H		 0 – 2 = -2

I		 0 – 2 = -2

J		 0 – 2 = -2

Possible courses of action:

- Divert manpower from D to either C or F.  Activity D is the only activity remaining in the project with positive slack.

- Crash any of the critical path activities C or F.  These should take the top priority over any of the other critical path activities which follow them.